## Slide 1: Functioning & Activities Update
Penni Hernandez

## Slide 2: Project Status
Started in January 2015
Collected Use Cases to drive requirements – Nutrition, OT, Health Outcomes, US Veterans Administration
Project group meeting every two weeks
Wide coverage of stakeholders

## Slide 3: Observables Model Application
Gleaned submitted use case examples
Test/model a handful concepts pulled from existing use cases
  Note exceptions as use cases for further analysis
  Note necessary extension of domains/ranges
Decision that the Model needed more development

## Slide 4: Observables Modeling
282097004
Ability to walk (observable entity)
Output of
710828008
Assessment of ability to walk (procedure)
Is about
Walking (qualifier value)
282144007
Able to walk (finding)
observes
specified by

## Slide 5: Fully define – Functional observable (observable entity)

## Slide 6: Goniometric range of movement of ankle joint (observable entity)
Unable to use “technique” in current WB

## Slide 7: 282144007|Able to walk (finding)

## Slide 8: Ability to walk with assistance (observable entity)
Permitted to use “precondition” currently?

## Slide 9: January 2016 Release Changes
Using only existing concept model
Add and fully define organizing concepts within a contained area
Make sure existing concepts are fully defined noting exceptions as use cases for further analysis
Add missing concepts needed to fully define existing concepts
January 2016 Release changes
  Review “pairs” of findings/observable entities
  Add missing concepts for a limited set of Functioning concepts: able, not able, difficulty, does, does not

## Slide 10: Plan for Future
Creation of a Technical preview Spring 2016 (dependent on Observables Model)
Continue Testing/modeling additional concepts pulled from existing use cases (100? 500?)
  Note exceptions as use cases for further analysis
  Note necessary extension of domains/ranges
Sign off from Head of Terminology for solution
Write up guidance
Functioning
  Phase 1 – Restructuring of existing hierarchy and identification and addition of new content (Initial work – January 2016)
  Phase 2 - Development, testing and documentation of concept model (June, 2017)
  Phase 3 – Implementation of new model to existing functioning content content (July 2018)