## Slide 1: SNOMED CT Content Roadmap July, 2015
Jim Case
Head of Terminology
Ian Green
Business Services Executive

## Slide 2: Roadmap Principles
Roadmap to be updated and issued every six months
  January and July each year
Roadmap to focus on next three years i.e. next six international releases
Roadmap to be ‘confirmed’ within year and ‘candidate’ beyond that
  Rescheduling/removing ‘confirmed’ items to done only in exceptional circumstances, due to likely significant impact, and will include member and end-user communication
  Rescheduling/removing ‘candidate’ items possible through discussion with Head of Terminology and Business Services Executive
  Roadmap will include Technology Previews when projects require such
In the event of delayed delivery of any project within year, the Business Service Executive and Head of Terminology will notify the Management Board and Member Forum within four weeks of the issue being identified

## Slide 3: Audience
Roadmap is aimed at all IHTSDO staff and stakeholders
Stakeholders including but not limited to:
  General Assembly
  Management Board
  Member Forum
  Existing Members and Affiliates
  Prospective Members and Affiliates
  Implementers
  Vendors
  Community of Practice
Subject to agreement from Management Board, the roadmap will also be published on the IHTSDO website

## Slide 4: Content Development Sources
Requests and ideas for SNOMED CT content development can come from many difference sources
Broadly there are four main sources
  IHTSDO content development projects
    Collaboration agreements (development and alignment of content)
    Strategic developments
  Member country content development projects
    Member priorities/Annual budget process
  SNOMED CT International Request Submission (SIRS)
    Members and Affiliates
  Maintenance
    Content quality enhancements
    Collaboration agreements (maintenance of content alignment)
    Routine maintenance

## Slide 5: Approach to content development
FOUNDATIONAL
LAYER
underpins all other SNOMED CT content
(Primary focus)
CONTENT
LAYER
Organisms
Anatomy
Devices
Substances & Drugs
SNOMED CT
CONTENT

## Slide 6: Focus of content developments
Strategic
  Collaboration agreements
  Developments fundamental to usability of the SNOMED CT product
  Content updates fundamental to SNOMED CT structure
Member led priorities
  Priorities submitted as part of the annual budgeting process
  Agreed list of member priorities as agreed by the Member Forum sub-committee
  Priorities reviewed internally and a delivery schedule developed
Quality assurance
  Routine authoring consistency based on standard guidelines
  Changes made to existing content highlighted through normal authoring activities
  Addressing content tracker items, where a quality issue has been documented and a solution identified

## Slide 7: Order of developments
Structural developments
  Scheduled as soon as authoring capacity allows, as these developments underpin all future content work and are necessary for future developments
Fundamental developments
  High impact to end users, and have been scheduled in the same way as structural developments
Reputational developments
  Represent known issues relating to high usage areas of content, and have been scheduled accordingly
  Correction to significant errors in content

## Slide 8: Strategic content projects justification
Drugs (pharmaceuticals) (structural) 17,000 concepts currently
  Required to provide SNOMED CT with the source data for representation of drugs, also required as the target for attribute values to model other content in SNOMED CT
  Both strategic and Member-led priority
Substances (structural) 26,000 concepts currently
  Required to act as the target of attribute vales for drugs and allergies
  Known area of inaccuracy within the terminology
  Aim is to ensure consistency and accuracy through alignment with existing external classifications
Devices (structural) 14,000 device concepts (+ 14,500 physical objects)
  Required to act as the target of attribute vales for Procedures, Situations and Clinical Findings
  Increasing global emphasis on Medical Devices representation through, for example, UDI (Universal Device Identifier) developments

## Slide 9: Strategic content projects justification
Anatomy (structural) 17,500 concepts currently
  Required for the attribute value target of procedures, findings, situations and observables, affects almost all content in SNOMED CT
  Alignment of SNOMED CT content to FMA
  Reengineering the anatomy hierarchy to ensure correct inheritance
Observable Entity (fundamental) 8,500 concepts currently
  Required to support recording and transmission of clinical observations unambiguously
  Currently a primitive hierarchy
  Provides the model for specifying functioning and laboratory content
Situations (reputational) 4,000 concepts
  Required work to differentiate in existing hierarchy between procedure with context and observation results content
  Known area of quality issues in a high use content area Requires separation of content into procedures with content and observation results

## Slide 10: Strategic content projects justification
Allergy project (fundamental)
  Required for successful clinically safe implementation of SNOMED CT and to support decision support applications
  Updating of editorial guidance and content alignment with solution for findings, substances,
Organisms (structural) – 30,000 concepts
  Updating and redesign of existing organism content
  Implementation of new concept model for organism representation
  Required for future work on laboratory medicine, infectious disease and genetics

## Slide 11: Collaboration-led content developments
International Council of Nurses (ICN)
  Nursing content and linkage table creation
    Diagnosis
    Intervention
Institut national de la santé et de la recherche médicale (INSERM) - Orphanet (classification of rare diseases)
  Review and gap analysis of existing SNOMED CT content
  New content added, alignment of text definitions, linkage table creation
World Health Organisation (WHO)
  ICD-11 – alignment/addition of content through internal review and external clinical review
  Common ontology
    Development of a shared common ontology with WHO
    Addition/revision of SNOMED CT content to ensure the implementability of ICD-11 through the common ontology layer

## Slide 12: Collaboration-led content development
World Organization of Family Doctors (WONCA)
  IFP/GP subset
  ICPC-2 to SNOMED CT map
American Dental Association (ADA)
  Provision of new dental content, and revision of existing content
  Focus is dental findings and dental anatomy, with a longer term goal to include procedures
Kaiser Permanente (Convergent Medical Terminology - CMT)
  Provision of candidate SNOMED CT content for review/addition to the SNOMED CT International Edition
  Publication of candidate SNOMED CT content for the benefit of Members as a complete listing
Regenstrief Institute (LOINC)
  Provision of content to support the interoperability between SNOMED CT and LOINC
  Publication of expression libraries relating alignment of LOINC expressions to SNOMED CT

## Slide 13: Release schedules for the next 3 years
The following schedules are based on known agreed work items, either in progress or with plans well advanced
The content projects are listed where developments are undertaken. Once the changes have been made the assumption is that future authoring in these areas will be classed as business as usual

## Slide 14: Structural (foundational)
2016
2017
2018
Devices
Drugs
Organisms
Substances
ALPHA RELEASES (TECHNOLOGY PREVIEWS)
Anatomy

## Slide 15: Fundamental
2016
2017
2018
ICD-11
CMT
Situations
Allergies
Observable entity
Functioning
ALPHA RELEASES (TECHNOLOGY PREVIEWS)
CMT (BAU)

## Slide 16: Reputational
2016
2017
2018
Event, condition and episode
Dentistry
Nursing
Orphanet
LOINC
ALPHA RELEASES (TECHNOLOGY PREVIEWS)
Nursing (BAU)
Dentistry (BAU)

## Slide 17: Business as usual activities
Activity
Routine SIRS requests
Routine content maintenance
Alignment of content with external sources
Quality assurance of content (review and update of content)
Freshdesk queries
Updating derivative products linked to Collaborative agreements
Subset maintenance
ICD-0 maintenance
SNOMED CT to ICD-10 map
CMT, dentistry & nursing updates – 2017 onwards

## Slide 18: Redesign projects – (phases & target release dates)
Situations
  Phase 1 – Within Situations hierarchy, identification of procedure with context and observation results
  Phase 2 – Move Observation results to Observable Entity hierarchy, and restructure Situations hierarchy (January, 2017)
Observables
  Phase 1 – Development, testing and documentation of Observables model (complete)
  Phase 2 – Pilot of scalable authoring of observables content using new model (April 2016)
  Phase 3 – Modeling of existing Observables content (January 2017)
Functioning
  Phase 1 – Restructuring of existing hierarchy and identification and addition of new content (Initial work – January 2016)
  Phase 2 - Development, testing and documentation of concept model (June, 2017)
  Phase 3 – Implementation of new model to existing functioning content content (July 2018)
Event, condition, episode project
  Phase 1 – Combined disorders X with Y, X due to Y (January, 2016)
  Phase 2 – Allergy / allergic reaction / allergic disorder (January, 2017)
  Phase 3 – Life phases (To be defined)

## Slide 19: Member content priorities
Priorities will be identified annually by members and submitted through the Member Forum
The priorities will be reviewed by Member Forum subcommittee, and a proposed list of priorities will be submitted to the internal content team for review
All priorities will be specified in a Project Charter document by the submitter
All Project Charters will be reviewed by the Business Service Executive and Head of Terminology and a delivery plan specified

## Slide 20: Future content issues
Potential content development areas for future releases driven by internal or member requirements
  Genomics/genetics
  Cancer synoptic reporting
  Diagnostic imaging
  Procedure alignment to external classifications
Systematic quality assurance of all SNOMED CT content using internal and external resources
Implementation of new tooling will assist in increase the ability to quality assure content. Initially, we expect a productivity drop with the implementation of a new authoring environment