## Slide 1: Drug Concept Model and Substance Redesign Update for EAG
17 February 2017

## Slide 2: Drug Concept Model Update

## Slide 3: Current status
First iteration of Editorial Guidelines for modeling and terming
  Released to Project Group on 2-Feb; also notified EAG, MAG, CMAG of availability
  Review period closed 14-Feb; we received 51 comments from six countries
  Comment topics included:
    Terming patterns refinements
    Requests for additional examples to illustrate the guidelines
    Groupers that will be included
    Exclusion of primitive concepts
    Normalization of product strength
    Source of content for ongoing maintenance
  Call with Project Group yesterday to agree on resolution for each comment (resolved issue log can be shared)

## Slide 4: Current status, continued
Development of second iteration of editorial guidelines is underway
  Plan to release to the Project Group in early March
Continuing to prototype and test proposed changes
Identification of tasks/dependencies for deployment plan targeting completion in 2018-Jan
  Including identification of work items that are candidates to be completed for 2017-July
  Plan forout of scope content or concepts that cannot be fully defined

## Slide 5: Model for national extension
Planning for development of model and editorial guidelines that could be used by a national extension

## Slide 6: Extension of Causative agent to include Product concepts

## Slide 7: Current status
No change since last month
Review of relationships currently using substance concepts as attribute values
  Identify instances that refer to product rather than substance
  Establish tooling test branch
  Dependencies
  Updated product concepts
  Updated allergy to X concepts

## Slide 8: Substance Hierarchy Redesign

## Slide 9: Current status
Documentation/proposal posted for several aspects of project, including:
  Use cases
  Review of work prior to 2016
  Salts, bases, and derivatives
  Groupers (structural, disposition, and role)
Plan for dispositions
  Much of the substance work is dependent on the solution for dispositions
  A detailed proposal has been posted on EAG site for review and comment
  After a solution has been agreed, we will distribute appropriate notifications re: upcoming changes