## Slide 1: Drug and Substance Project Update
Toni Morrison
Sr. Terminologist

## Slide 2: Drug Project Update

## Slide 3: Approach
Focus
  On strength and possibilities to change
  Take big but wise steps to minimize impacts
  Develop a faster path to remove adoption, regulation and compliance barriers
Involvement
  Established project group
    Request 2 members per country as project group representatives, (still time to join in contact Toni Morrison TMO@SNOMED.org)
  Established working group
  Secured expertise from termMed
  Extend pharmacy expertise
Forge Ahead

## Slide 4: Progress and Focus
Agreement on a interim solution for representation of numeric values
  Functionality to support Concrete Domains is being considered by the MAG as part of the wider question of enhancing SNOMED's ability to support Description Logic in general.
  Sub-group who have been meeting fortnightly detailed here: https://confluence.ihtsdotools.org/display/mag/SNOMED+CT+OWL2+EL+Logic+Profile
Position Statement relative to International Third Party Standards
  http://www.snomed.org/news-articles/position-statement-snomed-ct-pharmaceutical-product-concept-model-and-content-relative-to-international-third-party-standards
  Position will be revisited every 6 months or as needed as project evolves

## Slide 5: Progress and Focus, cont.
  National Extension RFP to progress national level concept model
  Posted April 5, 2017
Iterative development and documentation of Editorial Guidelines for Terming and Modeling
  Iteration 3 distributed to PG last week for review and comment

## Slide 6: General Assumptions
Concept model will conform to description logic principles, including use of the classifier to organize the concepts in the hierarchy
After classification, the top level concepts in the hierarchy will primarily be grouper concepts
Concept model will include attributes necessary to define the concepts to ensure consistent and reproducible modeling of concepts
Concept model will support representation of numeric values as SNOMED CT concepts
Concept model will not support universal restrictions
Concept model will not support nesting

## Slide 7: General Assumptions, cont.
Concept model will be compatible with IDMP
Concepts in the |Pharmaceutical / biologic product| hierarchy shall be sufficiently defined using proximal primitive modeling methodology unless explicitly noted as an exception in the editorial guidelines
The content in the |Pharmaceutical / biologic product| hierarchy is not intended to support prescribing use cases or to eliminate the need for a national extension

## Slide 8: 2017-July
Incremental positive changes for these concept classes:
  Medicinal Product (MP) - An abstract representation of the intended active ingredient for a drug product
  Medicinal Product Form (MPF) – An abstract representation of active ingredient and site-based dose form for a drug product.
  Clinical Drug (CD) - An abstract representation of the intended active ingredient, basis of strength substance (BoSS), strength, and manufactured dose form of a drug product.

## Slide 9: July 2017 Release Content Changes
  New hierarchies
  Number (qualifier value) - descendants only
    Existing concepts updated (n ≈ 20)
    New concepts created (n ≈ 625)
  Unit of presentation (unit of presentation) - root concept and descendants
    New concepts created (n ≈ 50)
  New semantic tags
  unit of presentation
  medicinal product
  medicinal product form
  clinical drug

## Slide 10: July 2017 Release Content Changes
  New attribute types
  Has basis of strength substance
  Has presentation strength numerator value
  Has presentation strength numerator unit
  Has presentation strength denominator value
  Has presentation strength denominator unit
  Attribute type changes
  |Has dose form|
    Existing FSN and Preferred Term will be inactivated and replaced with |Has manufactured dose form|

## Slide 11: July 2017 Release Content Changes
  Medicinal product (MP)
  Descriptions for ≈ 1300 existing concepts will be updated in accordance with new terming guidelines, including new "virtual medicinal product" semantic tag
  Existing stated parents and definition status will be retained
  Missing |Has active ingredient| attributes will be added; errors in existing content will be corrected as they are identified
  Medicinal product form (VMPF)
  Descriptions for ≈ 1300 existing concepts will be updated in accordance with new terming guidelines, including new "virtual medicinal product form" semantic tag
  Existing stated parents and definition status will be retained
  Missing |Has active ingredient| and |Has manufactured dose form| attributes will be added; errors in existing content will be corrected as they are identified

## Slide 12: July 2017 Release Content Changes
  Clinical drug (CD)
  Descriptions for ≈ 3000 existing concepts representing oral tablets and oral capsules will be updated in accordance with new terming guidelines, including new "virtual clinical drug" semantic tag
  Existing stated parents and definition status will be retained
  Missing |Has active ingredient| and |Has manufactured dose form| attributes will be added
  New |Has basis of strength substance|, |Has presentation strength numerator value|, |Has presentation strength numerator unit|, |Has presentation strength denominator value|, and |Has presentation strength denominator unit| attributes will be added

## Slide 13: Substance Project Update

## Slide 14: Sept 2016 - March 2017 Substances
Formalize Substance Requirements in SOW, gain resource from NHS Digital to progress those initiatives
  Review documentation of previous Substance work
  Develop Editorial Guidelines
  Develop Substance project plan and schedule to span the next 2 International Releases.
Progress CRS requested updates per SLA agreement and make corrections of errors/omissions identified as result of other work (e.g. drugs, allergies)

## Slide 15: Sept 2016 - March 2017 Substances
Modeling of Concepts Representing Dispositions and Roles
  Testing of the changes to improve the representation of dispositions is underway at this time; deployment date forecasted for Jan 2018
  Testing of options for remodeling of concepts representing roles that cause incorrect inferences in the Substance as well as other hierarchies is under discussion; deployment date tentatively forecasted for Jan 2018

## Slide 16: Closing Remarks
We will continue to proceed in building on our accomplishments in the project and well as incorporating lessons learned to make greater gains on improvement and progress
SNOMED International welcomes all opportunities to discuss partnerships in order to advance our drug content and quality for our members and stakeholders

## Slide 17: Questions
In order to provide all with solid and clear answers to a complicated topic please direct questions to drugs@snomed.org so that we can provide timely and comprehensive responses that can be shared across AGs and SIGs